## Day-Wise Implementation Plan
Day | Module / Track | Focus Area, UI Screens & Functional Scope | API Integration & Endpoints (swadhaar-admin-repo) | Deliverables & Verification Criteria | Daily Hours
Day 1 | Phase 1: Foundation & Theming Phase 1: Layout & Core Primitives | Admin UI Branding & Theming to Swadhaar: • Establish brand tokens in customTheme.tsx matching Swadhaar Learner App: Primary (#E6873C), Secondary/Navy (#1C2B4A), Surface (#FFFFFF), Canvas (#F5F5F5). • Swadhaar Logo in header, PWA manifest favicon & metadata. • Global typography setup (Inter/Poppins) & CSS variables. • Host-based Tenant Detection integration (leveraging tenant detection hook from Shikshagraha branding KI). • Dark / Light Theme preference persistence. • Strict Zero-Inline-Styles enforcement & Base UI primitives: SwadhaarStatCard, LifecycleChip, SDBVHierarchyFilter. Layout Architecture & SwadhaarDataTable Primitive: • Build full admin shell: Collapsible Sidebar, App Header, and Breadcrumbs. • Dynamic Navigation Menu supporting RBAC visibility (Admin, Creator, Reviewer). • Header integration: Swadhaar logo, global search, language switcher (en, mr, hi via next-i18next), and profile avatar. • Master SwadhaarDataTable primitive: debounced search, column sorting, row multi-select checkboxes, server-side pagination, empty state illustrations, and loading skeletons. | TenantService.ts, Interceptor.ts: • GET /api/v1/tenant/read (Resolve tenant ID & channel info) • GET /api/v1/tenant/branding/{tenantId} (Fetch logo, brand colors, favicon config) • Configure Axios/Fetch interceptor to attach X-Tenant-Id, X-Channel-Id, and Bearer tokens to all requests. MasterDataService.ts, LayoutService.ts: • GET /api/v1/user/profile (Fetch authenticated user info & active roles for layout avatar) • GET /api/v1/menu/navigation (Retrieve authorized nav sections based on user role) • Locale message catalog loader for next-i18next. | • Theme engine fully operational matching learner-web-app. • Tenant detection hook dynamically applies Swadhaar branding. • Zero-inline-style lint rule passing. • Responsive layout shell with mobile drawer & desktop sidebar. • Reusable SwadhaarDataTable ready for Users, Cohorts, and Content tables. | 8.5 hrs
Day 2 | Phase 1: Auth & Session Management Phase 1: Role & Access Management (RBAC) | Admin Login with OTP (Learner App Parity): • Dedicated Admin Login screen (/login) with Swadhaar brand card layout. • 10-digit mobile number input with regex validation. • 6-digit OTP entry screen with 30-second resend cooldown timer. • Role-aware post-login redirect (Super Admin/Admin -> /dashboard, Content Creator -> /content/courses, Reviewer -> /content/review-queue). • JWT token refresh handling, session storage, and auto-logout on token expiration. • Keycloak SSO alignment & RouteGuard (/components/RouteGuard.tsx). Role & Access Management (RBAC): • Role Definitions: Super Admin, Admin, Content Creator, Reviewer, Report Viewer. • Permission Matrix UI (/access/permissions): Interactive Grid (Roles x Permission Modules: User Mgmt, Cohort Mgmt, Content Authoring, Review & Publish, Notifications, Analytics) with toggle switches. • Role Assignment UI: Single and bulk user role assignment modal. • Frontend Route & Component Permission Guards (e.g. <PermissionGate permission='CONTENT_PUBLISH'>). • RBAC Audit Log (/access/audit-log): Table displaying actor, action, timestamp, target user, and before/after permission delta. | LoginService.ts, Interceptor.ts: • POST /api/v1/auth/otp/send (Body: { phone: string, app: 'admin' }) • POST /api/v1/auth/otp/verify (Body: { phone: string, otp: string } -> Returns { token, refreshToken, user: { id, roles, tenantId } }) • POST /api/v1/auth/refresh-token (Silent background refresh) • POST /api/v1/auth/logout (Revoke session). RbacService.ts: • GET /api/v1/rbac/roles (Fetch all system roles & definitions) • GET /api/v1/rbac/permissions (Fetch permission tree by domain) • PUT /api/v1/rbac/matrix/update (Update role-permission mappings) • PUT /api/v1/rbac/user-roles/{userId} (Assign/revoke roles for user) • GET /api/v1/rbac/audit-logs (Paginated audit trail with date/actor filters). | • Functional OTP login flow with 30s countdown. • RouteGuard redirects unauthorized users to /login. • Role-based landing page routing verified. • Complete Permission Matrix UI with real-time toggle feedback. • PermissionGate guards restricting buttons/routes based on active user's roles. • Audit log viewer functioning. | 8.0 hrs
Day 3 | Phase 1: User Management Core | User Management (CRUD & SDBV): • Screen N1: Users Directory (/users) with SDBV Hierarchy cascading filters (State -> District -> Block -> Village/Branch) and Group SDBV filter. • Table columns: Name, Employee ID, Phone (mandatory), Gender, Location (State/District/Block), Role, Status. • Screen P2: User Create/Edit Modal (/users/create): - Mandatory phone field with uniqueness & 10-digit validation. - Gender dropdown (Male, Female, Other, Prefer not to say - optional). - Cascading SDBV dropdowns with program/branch mapping. • Screen P3: User Detail Profile (/users/[id]) with 4-card layout (Location, Role, Cohort Memberships, Review Relationships). • User Activate / Deactivate (soft delete/suspend without data loss). | UserService.ts, MasterDataService.ts: • POST /api/v1/user/search (Query with SDBV filters, role, status, page, limit) • POST /api/v1/user/create (Body: { name, phone, gender, sdbv: { state, district, block, village }, program, role }) • PUT /api/v1/user/update/{id} (Update user profile attributes) • PUT /api/v1/user/status/{id} (Body: { status: 'active' ¦ 'suspended' }) • GET /api/v1/master/sdbv/hierarchy (Cached via TanStack Query). | • Users directory rendering with cascading SDBV filters. • User create modal validates mandatory phone & optional gender. • Profile view and soft-delete toggle operational. | 8.5 hrs
Day 4 | Phase 2: Bulk Operations & Review Mapping | Bulk User Creation & User-Reviewer Mapping: • Screen N2: Bulk User Upload & Validation Wizard (/users/bulk-upload). • Step 1: Download pre-formatted sample CSV template (with State, District, Block, Village, Phone, Gender, Role, Program headers). • Step 2: Drag-and-drop CSV uploader with client-side syntax pre-validation. • Step 3: Interactive validation results table (N rows valid, M rows failed with exact cell error reasons highlighted). • Step 4: 'Download Failed Rows CSV' button for offline fixing & 'Proceed to Import' button for valid rows. • Screen P8: Add User to Review Modal (assign user to dedicated ARM/DI reviewer). | BulkUserService.ts, UserService.ts: • POST /api/v1/user/bulk/upload (Multipart CSV file upload) • POST /api/v1/user/bulk/validate (Validate parsed CSV rows against DB schemas) • GET /api/v1/user/bulk/job/{jobId} (Poll job progress & fetch failed rows) • POST /api/v1/user/review-mapping (Body: { userId, reviewerId, notes }). | • Multi-step CSV upload wizard with progress bar. • Error CSV generator exporting rows with error messages. • Reviewer mapping modal updates user relationships. | 8.5 hrs
Day 5 | Phase 2: Cohort Management & Mapping Phase 2: Group Builder & In-Group Roles | Cohort / Group Management (Core & Lifecycle): • Screen N4: Cohorts Directory (/cohorts) with SDBV filter, status tabs, and members/reviewers counters. • Create/Edit Cohort Modal: Cohort name, description, SDBV operational scope, auto-enrol rules. • Cohort-Course Mapping UI: Assign learning courses and learning paths to a cohort; view cohort completion %. • Cohort Lifecycle & Archive UI: Rename 'Status' to 'Lifecycle State', dedicated Archive Icon in action menu, Archive Cohort action with soft-hide from active roster & Restore action. • Cohort Analytics snapshot: aggregated completion %, active member count. Two-Panel Group Builder & Group Detail: • Screen N7b: Two-Panel Group Builder (/cohorts/builder): - Left Panel (User Pool): Cascading SDBV filters (State/District/Block), program filter, search input, multi-select checkboxes, and 'Add Selected (N) to Group' action. - Right Panel (Group Configuration): Group Name, description, and selected member list. Each member has a per-member in-group role selector: Learner, Reviewer, or Both (defaults to Learner). • Screen N6: Group Detail View (/cohorts/[id]): Header stats (Total, Learners, Reviewers), Members roster with in-group role badges, and Course assignments tab. • Screen N5 (Edit Group modal) & N3/N8 (Confirmation dialogs with safe deletion messaging). | CohortService.ts: • GET /api/v1/cohort/list (Filters: sdbv, status, page, limit) • POST /api/v1/cohort/create (Body: { name, description, sdbvScope, autoEnrol }) • PUT /api/v1/cohort/{id}/update • POST /api/v1/cohort/{id}/course-mapping (Body: { courseIds: string[] }) • PUT /api/v1/cohort/{id}/lifecycle (Body: { state: 'active' ¦ 'archived' }) • GET /api/v1/cohort/{id}/analytics-summary. CohortService.ts, UserService.ts: • GET /api/v1/user/search (Fetch filtered roster for left panel) • GET /api/v1/cohort/{id}/members (Fetch existing group members with in-group roles) • PUT /api/v1/cohort/{id}/members-with-roles (Body: { members: [{ userId, roleInGroup: 'Learner' ¦ 'Reviewer' ¦ 'Both' }] }) • DELETE /api/v1/cohort/{id}/member/{userId}. | • Cohorts table with SDBV filters and Course-mapping modal. • Archive/Restore cohort lifecycle actions verified. • Cohort completion stats displayed. • Interactive 2-panel builder transferring users with role selectors. • Cohort detail screen displaying members split by in-group role. • Member removal confirmation dialog functioning. | 8.5 hrs
Day 6 | Phase 2: Notifications & Alerts | Notification & Alert Management (Advanced): • Screen /notifications: Notification Center & Delivery Dashboard. • Notification Creation Wizard: Title, body copy, media attachment, target audience (by Role, Cohort, or SDBV hierarchy). • Delivery Channels: In-app bell notification, Push (FCM), and SMS integration toggle. • Notification Templates UI: CRUD for reusable notification templates with dynamic placeholders (e.g. {{userName}}, {{courseTitle}}, {{deadline}}). • Scheduler UI: One-time future date/time delivery & recurring schedules (daily, weekly). • Delivery Status Analytics: Real-time Sent, Delivered, and Failed counts. • Alert Rules Engine: Configure automated triggers (e.g. 'Alert cohort when course completion < 20% after 7 days'). | NotificationService.ts, NotificationTemplateService.ts: • GET /api/v1/notification/list (Paginated notifications with status filters) • POST /api/v1/notification/create (Body: { title, body, channels: ['in-app', 'push', 'sms'], target: { type, ids }, scheduledAt }) • GET /api/v1/notification/templates • POST /api/v1/notification/templates/create • GET /api/v1/notification/{id}/delivery-status • POST /api/v1/notification/rules (Configure threshold alert triggers). | • Notification creation form with multi-channel and audience selection. • Template manager with dynamic variable insertion. • Delivery status counters (Sent/Delivered/Failed) operational. | 8.5 hrs
Day 7 | Phase 3: Content Taxonomy & Filtering | Content Taxonomy & Topic/Subtopic Filters: • Screen /content/taxonomy: Taxonomy Tree Management UI. • CRUD for Topics and Subtopics with hierarchical parent-child relationships. • Drag-and-drop tree reordering for topics and subtopics. • Taxonomy Import tool: Batch import taxonomy trees from CSV / JSON. • Content-to-Taxonomy Mapping: Assign multiple topics/subtopics to content items. • Orphan Detection: Flag content items missing taxonomy mappings. • Dynamic Content Filtering Engine: Dynamic Subtopic dropdown (populated based on selected Topic), Content-Type filter showing only types with uploaded assets, filter persistence in Zustand, and 'Clear All Filters' single-click button. | TaxonomyService.ts, FrameworkService.ts: • GET /api/v1/framework/read/{frameworkId} (Fetch channel taxonomy tree) • POST /api/v1/taxonomy/topic/create (Body: { name, code, parentId }) • PUT /api/v1/taxonomy/topic/{id}/update • POST /api/v1/taxonomy/reorder (Body: { orderedIds: string[] }) • POST /api/v1/taxonomy/import (Multipart CSV/JSON import) • GET /api/v1/taxonomy/orphans (List unmapped content items). | • Interactive taxonomy tree with node creation & drag-reorder. • Cascading Topic -> Subtopic filter dynamically loading children. • Orphan check report highlighting unclassified content. | 8.5 hrs
Day 8 | Phase 3: Content-Type Config & Dynamic Schemas Phase 3: Course Catalog & Form Updates | Content-Type Configuration & Metadata Forms: • Screen /content/content-types: Admin Content-Type Registry. • Registry of supported content types (Video, PDF, Assessment, Audio, Interactive HTML5). • Per-Type Metadata Schema Builder: Configure custom metadata fields (field type, label, tooltip, required flag, validation regex, default value) for each content type. • Dynamic Form Renderer Component (DynamicMetadataForm.tsx): Dynamically generates input controls and validations based on JSON schema. • Type-specific validation rules (e.g. video minimum duration >= 30s, PDF max size <= 25MB). • Learner Display Configuration: Toggle which metadata fields appear to learners in the Learner App. Course Catalog & Form Updates (New Fields, Tooltips, Auto-save): • Screen L1: Course Catalog (/content/courses) with All, Published, and Drafts tabs. • Archive & Lifecycle UI: Rename 'Status' to 'Lifecycle State', Archive Icon in row actions, Lifecycle states: Draft -> Review -> Published -> Archived -> Deleted. • Screen L2: Course Overview Metadata Form (/content/courses/create): - New Metadata Fields: Difficulty level, target audience, prerequisite course, estimated duration (aggregated). - Contextual help tooltips on all fields. - Field-level regex and boundary validations. - Single language select (Hindi, Marathi, English) per course. - Rich text editors for Course Objectives & How It Works. - Periodic Draft Auto-save with visual indicator ('Saved at 14:32'). | ContentTypeService.ts: • GET /api/v1/content-type/registry (List active content types) • POST /api/v1/content-type/registry/create • GET /api/v1/content-type/{type}/schema (Fetch JSON schema for type) • PUT /api/v1/content-type/{type}/schema (Update field definitions & validations) • PUT /api/v1/content-type/{type}/display-config (Set learner visibility flags). ContentService.ts, CoursePlannerService.ts: • GET /api/v1/content/course/list (Filters: lifecycleState, language, search, page) • POST /api/v1/content/course/create (Body: { title, audience, difficulty, duration, language, objectives, howItWorks }) • PUT /api/v1/content/course/draft/{id} (Periodic auto-save endpoint) • PUT /api/v1/content/course/{id}/lifecycle (Archive / restore / delete). | • Content-type management registry operational. • Schema builder allowing dynamic field configuration. • DynamicMetadataForm rendering compliant forms from backend schema. • Course catalog displaying lifecycle chips and archive action. • Course overview form with difficulty/audience fields and tooltips. • Draft auto-save timer saving changes without page reload. | 8.5 hrs
Day 9 | Phase 3: Course Structure & Units Builder Phase 3: Section Content & Question-Set Builder | Course Structure & Units Builder: • Screen L3: Course Curriculum Builder (/content/courses/[id]/builder). • Ordered Sections Tree with Move Up / Move Down sequence reordering. • Section Duration Calculation: Aggregates runtime of all child videos and reading time of PDFs. • Course-Level Units: FAQs, Course Summary, Course Assessment, Transition screens. • + Add Section Modal: Section title, target duration, learning objectives. • Course Completion Rules: Configure passing threshold (default 70% passing score). • Action buttons: 'Save as Draft', 'Preview as Learner', and 'Submit for Review'. Section Content Editor & Question-Set Form Updates: • Screen L4: Section Content Editor (/content/sections/[id]/edit): - Structured Pedagogical Blocks: Intro -> Hook -> Video Watch -> Concept -> Analysis. - Reorderable typed blocks: Text, Hook, Concept, Analysis, Video, Image. - Rich text formatting toolbar (bold, italic, list, links). • Screen L9 & L10: Assessments Library & Question-Set Builder (/content/assessments/[id]/builder): - Question Types: MCQ Single, MCQ Multi, True/False, Short Answer. - Bloom's Taxonomy Tag dropdown (Remember, Understand, Apply, Analyze, Evaluate). - Contextual Tooltips, Hint text, and Answer Explanation fields. - 70% Passing Rule setting and timer configuration. | ContentService.ts: • GET /api/v1/content/course/{id}/hierarchy (Fetch full tree: units, sections, assets) • POST /api/v1/content/course/{id}/section/create • PUT /api/v1/content/course/{id}/reorder-sections (Body: { sectionOrder: string[] }) • PUT /api/v1/content/course/{id}/units • GET /api/v1/content/course/{id}/validate-publish (Verify minimum 1 section & 1 assessment). ContentService.ts, AssessmentService.ts: • GET /api/v1/content/section/{id} • PUT /api/v1/content/section/{id}/update (Save pedagogical blocks array) • GET /api/v1/assessment/list • POST /api/v1/assessment/create • PUT /api/v1/assessment/{id}/questions (Body: { questions: [{ type, text, options, correctOption, hint, explanation, bloomsTag }] }). | • Interactive course structure tree with Move Up/Down reordering. • Automated duration aggregation updating course total. • Validation check ensuring course structure completeness. • Pedagogical section block editor saving structured blocks. • Question-set builder supporting Bloom's tags, hints, and explanations. • Passing threshold validation enforced at 70%. | 8.5 hrs
Day 10 | Phase 3: Media Handling & Central Library | Media Handling & Central Library (Videos, PDFs, Embeds): • Central Media Library (/content/library) with tabbed views: Videos, PDFs, Images. • Screen L11 & L5: Videos Library & Video Uploader: - MP4 video upload with upload progress, transcoding status, and auto-generated thumbnail. - YouTube Video Embed: URL input with live embed preview and oEmbed metadata fetch (title, duration). • Screen L12 & L5b: PDFs Library & Document Uploader: - Drag-and-drop PDF file uploader, page count detector, estimated read time, and in-portal PDF viewer preview. - Learner download permission toggle. • Image handling: upload, crop/resize modal, and alt-text for a11y. • Screen L4b: Media Picker Modal (reuse media across sections). | MediaService.ts: • POST /api/v1/media/upload (Chunked multipart upload for MP4/PDF/images) • GET /api/v1/media/library (Search by filename, media type, tags, usage) • POST /api/v1/media/youtube-embed (Body: { url } -> returns title, thumbnail, duration) • GET /api/v1/media/{id}/transcode-status • GET /api/v1/media/{id}/courses-usage (List courses referencing this media). | • Multi-format media uploader with transcoding indicator. • YouTube embed card previewing video and auto-filling duration. • In-portal PDF previewer with pagination controls. | 8.5 hrs
Day 11 | Phase 4: Bulk Content Upload & Validation | Bulk Content Upload + Validation Engine: • Screen /content/bulk-upload: Bulk Content Import Wizard. • CSV / Zip Upload: Support batch upload containing course metadata CSV + zipped media assets (videos, PDFs, images). • Pre-upload Validation Engine: - CSV schema check (required columns: title, topic, language, duration, mediaFilename). - Media existence check: Verifies all mediaFilename entries exist in the ZIP package. - Duplicate title and code check against existing catalog. • Interactive Preview Before Commit: Table preview of parsed records with error rows highlighted in red and valid rows in green. • Download Error Report: Downloadable CSV containing failed row indices and explicit error reasons. • Row-by-row batch import progress bar. | BulkContentService.ts: • POST /api/v1/content/bulk/upload (Multipart upload for metadata CSV + assets ZIP) • POST /api/v1/content/bulk/validate (Trigger validation job) • GET /api/v1/content/bulk/job/{jobId} (Poll job progress, fetch valid count, error count, and error summary) • GET /api/v1/content/bulk/job/{jobId}/errors.csv (Download failed rows CSV) • POST /api/v1/content/bulk/job/{jobId}/commit (Commit valid items to catalog). | • ZIP + CSV batch content uploader operational. • Pre-validation engine detecting missing media and duplicate codes. • Error report generator and commit confirmation working. | 8.5 hrs
Day 12 | Phase 4: Content Review & Publish Workflow Phase 4: Content Versioning & Lifecycle | Content Review & Publish Workflow (Creator -> Reviewer -> Publish): • Workflow States: Draft -> Submitted for Review -> Changes Requested -> Approved -> Published. • Creator Submission Flow: Creator submits course draft with changelog notes; auto-notifies assigned Reviewers. • Screen /content/review-queue: Reviewer Dashboard displaying pending queue sorted by submission date and priority. • Interactive Review Workspace: - Full course & assessment preview. - Inline commenting on specific course sections and question blocks. - Actions: 'Approve Content', 'Request Changes' (with mandatory comment thread), or 'Reject'. • Admin Final Publish: Publish action gated strictly to Admin / Super Admin roles. • Workflow Audit Trail: Detailed drawer displaying entire state timeline, timestamps, actors, and review comments. Content Versioning, Archive & Delete Lifecycle: • Version History UI (/content/courses/[id]/versions): Chronological log of all published versions (v1.0, v1.1, v2.0). • Visual Diff Viewer: Side-by-side comparison of metadata, sections, and questions between any two versions. • One-Click Rollback: Restore any previous published version to Draft state. • Archive State: Move obsolete content to Archived; hidden from learner search and catalogues. • Soft Delete & Trash Bin (/content/trash): Soft-deleted items recoverable within configurable retention period (default 30 days). • Permanent Hard Delete: Double-confirmation modal strictly for Super Admins. • Retention Policy Configuration UI (configure retention window 7-90 days). | ContentWorkflowService.ts: • POST /api/v1/content/{id}/submit-review (Body: { changelog: string }) • GET /api/v1/content/review-queue (Filtered queue for Reviewers) • POST /api/v1/content/{id}/workflow/action (Body: { action: 'approve' ¦ 'reject' ¦ 'request_changes', comments: string }) • POST /api/v1/content/{id}/workflow/comments (Add section-level inline feedback) • POST /api/v1/content/{id}/publish (Gated to Admin) • GET /api/v1/content/{id}/workflow/history (Full audit timeline). ContentLifecycleService.ts: • GET /api/v1/content/{id}/versions (List version history) • GET /api/v1/content/{id}/diff?v1={v1}&v2={v2} (Fetch semantic diff between versions) • POST /api/v1/content/{id}/rollback/{versionId} (Rollback to selected version) • PUT /api/v1/content/{id}/archive (Move to archived state) • PUT /api/v1/content/{id}/restore (Restore from archive/trash to draft) • DELETE /api/v1/content/{id}/soft-delete • DELETE /api/v1/content/{id}/hard-delete (Permanent removal) • PUT /api/v1/content/retention-policy (Set retention window). | • Reviewer queue dashboard listing pending items. • Inline review commenting panel functioning. • Publish action strictly restricted to Admin role with audit trail. • Version history drawer showing visual diff between course revisions. • Rollback action restoring prior content snapshot. • Trash bin and archive lifecycle states fully testable. | 8.5 hrs
Day 13 | Phase 4: Admin Dashboard & Learning Paths Phase 4: Analytics Deep Dive & Final QA | Admin Dashboard (Operational Overview) & Learning Paths: • Operational Admin Dashboard (/dashboard): - 8 Executive KPI Stat Cards: Total Active Users, DAU/MAU Active Learners (7/30 days), Course Completion Rate %, Content Published (This Month), Pending Review Queue count, Notifications Sent counter. - SDBV Geographic Map View / Heatmap: Learner activity and completion breakdown by State and District. - Top 5 Courses Widget: Sorted by enrolment count and completion rate. - Quick Action shortcuts (+ User, + Cohort, + Course, + Notification). • Screen L6, L7, L8: Learning Paths & Enrolment: - Learning Paths Catalog (L6) & Path Sequence Builder (L7) with prerequisite lock rule ('Require >= 70% in Course N before Course N+1'). - Enrolment Modal (L8): Cohorts or Individual user assignments. Analytics Dashboard (Deep Dive), Export, i18n Audit & Deployment QA: • Screen /analytics: Deep Dive Analytics Reports Hub: - Learner Progress Report: User-level courses enrolled, completed, scores, and active dates. - Cohort Completion Report: Cohort completion %, average assessment score, dropoff point. - Course Engagement Report: Views, completion rate, average time spent, re-attempt frequency. - Assessment Performance: Question-level difficulty, discrimination index, distractor analysis. - Content Usage by Type: Interaction breakdown across Video, PDF, and Assessment. - Retention & Dropout Funnel: Enrolled -> Started -> 50% -> Completed. - SDBV Drill-down (State -> District -> Block) & Custom Date Range picker. - Export to CSV / Excel for all reports & Scheduled report email config. • 100% Localization Audit (en, mr, hi), Zero-Inline-Styles Audit, and Next.js Production Build QA. | DashboardService.ts, LearningPathService.ts: • GET /api/v1/analytics/dashboard/overview (KPI metrics & trend sparklines) • GET /api/v1/analytics/dashboard/sdbv-heatmap (State/District aggregate counts) • GET /api/v1/analytics/dashboard/top-courses • GET /api/v1/learning-paths/list • POST /api/v1/learning-paths/create (Body: { title, courses: [{ courseId, minScore: 70, unlockOrder }] }) • POST /api/v1/learning-paths/{id}/enrol (Body: { cohortIds, userIds }). AnalyticsService.ts, ReportExportService.ts: • GET /api/v1/analytics/reports/learner-progress (Filters: sdbv, cohort, dateRange) • GET /api/v1/analytics/reports/cohort-completion • GET /api/v1/analytics/reports/course-engagement • GET /api/v1/analytics/reports/assessment-analytics/{assessmentId} • GET /api/v1/analytics/reports/funnel • POST /api/v1/analytics/reports/export (Format: 'csv' ¦ 'xlsx' -> stream file download) • POST /api/v1/analytics/reports/schedule-email. | • Operational dashboard populated with KPI cards and SDBV heatmap. • Learning paths catalog with prerequisite course sequencing. • Enrolment modal linking cohorts to pathways. • Complete 6-report analytics suite with SDBV filters and CSV export. • 100% i18n translation coverage across English, Marathi, Hindi. • Clean production Next.js build (npm run build:swadhaar-admin). | 8.5 hrs
TOTAL | All 4 Phases (Admin, Content, Analytics, Core) | Comprehensive Swadhaar Admin Portal Implementation covering 100% of Formally Approved Scope across Admin, Content, and Analytics modules. | Integrated across 18 specialized service clients in apps/swadhaar-admin-repo/src/services/ connecting to 65+ REST endpoints. | Fully verified with Next.js 14 production build, strict zero-inline-styles theme compliance, and trilingual i18n support. | 120.0 hrs

## API Integration Matrix
Module / Domain | Feature / Capability | Method | API Endpoint Route | Frontend Service File | Request Payload / Query Params | Response Data & State Mutation
Tenant & Branding | Tenant Resolution & Config | GET | /api/v1/tenant/read | TenantService.ts | Headers: X-Channel-Id | Tenant ID, name, channel configs, active modules
Tenant & Branding | Brand Colors & Assets | GET | /api/v1/tenant/branding/{tenantId} | TenantService.ts | tenantId path param | Brand colors (primary #E6873C, secondary #1C2B4A), logo URL, favicon
Authentication | Send OTP to Phone | POST | /api/v1/auth/otp/send | LoginService.ts | { phone: '9876543210', app: 'swadhaar-admin' } | { success: true, message: 'OTP sent', cooldown: 30 }
Authentication | Verify OTP & Issue Session | POST | /api/v1/auth/otp/verify | LoginService.ts | { phone: '9876543210', otp: '123456' } | { token, refreshToken, user: { id, name, roles, tenantId } }
Authentication | Refresh Expired Token | POST | /api/v1/auth/refresh-token | LoginService.ts | { refreshToken: string } | { token: newAccessToken }
Authentication | Revoke Session / Logout | POST | /api/v1/auth/logout | LoginService.ts | Bearer Token | { success: true } -> Clear cookies/stores
RBAC & Access | Fetch All System Roles | GET | /api/v1/rbac/roles | RbacService.ts | - | List of roles (Super Admin, Admin, Creator, Reviewer, Report Viewer)
RBAC & Access | Fetch Permission Matrix | GET | /api/v1/rbac/permissions | RbacService.ts | - | Permission tree grouped by domain and action
RBAC & Access | Update Role-Permission Mappings | PUT | /api/v1/rbac/matrix/update | RbacService.ts | { roleId, permissions: string[] } | Updated role definitions; syncs to user permission stores
RBAC & Access | Assign / Revoke User Roles | PUT | /api/v1/rbac/user-roles/{userId} | RbacService.ts | { roles: string[] } | Updated user profile role badges
RBAC & Access | Fetch RBAC Audit Log | GET | /api/v1/rbac/audit-logs | RbacService.ts | Query: actor, targetUser, dateFrom, dateTo, page | Paginated audit logs with before/after state diff
User Management | Search / Filter Users Directory | POST | /api/v1/user/search | UserService.ts | { sdbv: { state, district, block, village }, role, status, page, limit } | { totalCount, users: [ { id, empId, name, phone, gender, sdbv, role, status } ] }
User Management | Create Single User | POST | /api/v1/user/create | UserService.ts | { name, empId, phone, gender, sdbv, program, role } | { success: true, userId, message: 'User created' }
User Management | Update User Profile | PUT | /api/v1/user/update/{id} | UserService.ts | { name, phone, gender, sdbv, program, role } | Updated user record
User Management | Activate / Deactivate (Soft Delete) | PUT | /api/v1/user/status/{id} | UserService.ts | { status: 'active' ¦ 'suspended' } | Updates user status chip
User Management | Bulk User Upload (CSV) | POST | /api/v1/user/bulk/upload | BulkUserService.ts | Multipart FormData: { file: CSV } | { jobId, status: 'processing', totalRows }
User Management | Poll Bulk Upload Job Status | GET | /api/v1/user/bulk/job/{jobId} | BulkUserService.ts | jobId path param | { status: 'completed', validCount, failedCount, failedRows: [] }
User Management | Assign User to Reviewer | POST | /api/v1/user/review-mapping | ReviewerMappingService.ts | { userId, reviewerId, notes } | Links reviewer to user profile (P3/P8)
Master Data | Fetch Cascading SDBV Hierarchy | GET | /api/v1/master/sdbv/hierarchy | MasterDataService.ts | Query: stateId?, districtId?, blockId? | { states, districts, blocks, villages, branches }
Cohort Management | List Cohorts & Groups | GET | /api/v1/cohort/list | CohortService.ts | Query: sdbv, status, page, limit | { totalCount, cohorts: [ { id, name, description, memberCount, courseCount, status } ] }
Cohort Management | Create Cohort | POST | /api/v1/cohort/create | CohortService.ts | { name, description, sdbvScope, autoEnrol } | { success: true, cohortId }
Cohort Management | Assign Courses to Cohort | POST | /api/v1/cohort/{id}/course-mapping | CohortService.ts | { courseIds: string[] } | Links courses to cohort; updates enrolled count
Cohort Management | Assign Members with In-Group Roles | PUT | /api/v1/cohort/{id}/members-with-roles | CohortService.ts | { members: [ { userId, roleInGroup: 'Learner' ¦ 'Reviewer' ¦ 'Both' } ] } | Updates cohort member roster and in-group role badges
Cohort Management | Archive / Restore Cohort Lifecycle | PUT | /api/v1/cohort/{id}/lifecycle | CohortService.ts | { state: 'active' ¦ 'archived' } | Toggles lifecycle state; moves between Active/Archive tabs
Notifications | List Sent & Scheduled Notifications | GET | /api/v1/notification/list | NotificationService.ts | Query: status, channel, dateRange, page | Paginated list with delivery counts
Notifications | Create & Dispatch / Schedule | POST | /api/v1/notification/create | NotificationService.ts | { title, body, channels: ['in-app', 'push', 'sms'], target: { type, ids }, scheduledAt } | { notificationId, status: 'scheduled' ¦ 'sent' }
Notifications | Notification Templates CRUD | GET / POST / PUT | /api/v1/notification/templates | NotificationTemplateService.ts | { title, templateBody, placeholders: ['userName', 'courseTitle'] } | Templates list / updated template
Notifications | Automated Alert Triggers | POST | /api/v1/notification/rules | NotificationService.ts | { triggerEvent: 'COMPLETION_BELOW_THRESHOLD', threshold: 20, afterDays: 7, cohortId } | { ruleId, active: true }
Taxonomy & Filters | Read Channel Taxonomy Tree | GET | /api/v1/framework/read/{frameworkId} | TaxonomyService.ts | frameworkId = 'swadhaar-framework' | Full taxonomy tree: Categories, Topics, Subtopics, and Terms
Taxonomy & Filters | Create / Update Topic & Subtopic | POST / PUT | /api/v1/taxonomy/topic | TaxonomyService.ts | { name, code, parentTopicId, description } | New or updated taxonomy node
Taxonomy & Filters | Drag-and-Drop Reorder Taxonomy | POST | /api/v1/taxonomy/reorder | TaxonomyService.ts | { parentId, orderedIds: string[] } | Persists updated taxonomy display order
Taxonomy & Filters | Batch Taxonomy Import | POST | /api/v1/taxonomy/import | TaxonomyService.ts | Multipart FormData: { file: CSV/JSON } | Parsed taxonomy nodes import summary
Taxonomy & Filters | Detect Orphan Content | GET | /api/v1/taxonomy/orphans | TaxonomyService.ts | - | List of content items without assigned topic/subtopic
Content Types | List Content-Type Registry | GET | /api/v1/content-type/registry | ContentTypeService.ts | - | List of supported content types (Video, PDF, Assessment, etc.)
Content Types | Get / Update Type Schema | GET / PUT | /api/v1/content-type/{type}/schema | ContentTypeService.ts | { fields: [ { name, label, type, required, tooltip, validationRegex } ] } | Dynamic schema applied to DynamicMetadataForm.tsx
Content Authoring | List Courses Catalog | GET | /api/v1/content/course/list | ContentService.ts | Query: lifecycleState, language, search, page | Paginated courses with section count, duration, lifecycle chip
Content Authoring | Create Course Overview | POST | /api/v1/content/course/create | ContentService.ts | { title, targetAudience, difficulty, language, objectives, howItWorks } | { courseId, lifecycleState: 'draft' }
Content Authoring | Periodic Draft Auto-Save | PUT | /api/v1/content/course/draft/{id} | ContentService.ts | { ...partialCourseData } | { savedAt: '2026-10-15T14:32:00Z' }
Content Authoring | Fetch Course Structure Hierarchy | GET | /api/v1/content/course/{id}/hierarchy | ContentService.ts | courseId path param | Tree structure: Units, Sections, Blocks, and Assessments
Content Authoring | Reorder Course Sections | PUT | /api/v1/content/course/{id}/reorder-sections | ContentService.ts | { sectionOrder: string[] } | Updated section display sequences
Content Authoring | Save Pedagogical Section Content | PUT | /api/v1/content/section/{id}/update | ContentService.ts | { blocks: [ { type: 'Intro'¦'Hook'¦'Video'¦'Concept'¦'Analysis', content, mediaId } ] } | Persisted section pedagogical blocks
Assessments | List Assessments | GET | /api/v1/assessment/list | AssessmentService.ts | Query: courseId, page, limit | Assessment catalog with question count and pass rate
Assessments | Create / Update Assessment & Questions | POST / PUT | /api/v1/assessment/{id}/questions | AssessmentService.ts | { passingScore: 70, timeLimit, questions: [ { type, text, options, answer, hint, bloomsTag } ] } | Updated assessment configuration
Media Handling | Upload Media File (MP4/PDF/Image) | POST | /api/v1/media/upload | MediaService.ts | Multipart FormData: { file, mediaType, title } | { mediaId, url, duration, thumbnailUrl, transcodeStatus }
Media Handling | Search Central Media Library | GET | /api/v1/media/library | MediaService.ts | Query: type, search, page, limit | List of uploaded assets with usage counts
Media Handling | YouTube Embed Metadata Fetch | POST | /api/v1/media/youtube-embed | MediaService.ts | { url: 'https://youtube.com/watch?v=...' } | { valid: true, title, duration, thumbnailUrl, embedHtml }
Bulk Content | Batch Upload Content (CSV + ZIP) | POST | /api/v1/content/bulk/upload | BulkContentService.ts | Multipart FormData: { csvFile, zipFile } | { jobId, totalRecords, status: 'validating' }
Bulk Content | Fetch Bulk Validation Status & Errors | GET | /api/v1/content/bulk/job/{jobId} | BulkContentService.ts | jobId path param | { validCount, errorCount, errors: [ { row, field, reason } ] }
Bulk Content | Commit Valid Content Batch | POST | /api/v1/content/bulk/job/{jobId}/commit | BulkContentService.ts | - | { importedCount, message: 'All valid records published/drafted' }
Review Workflow | Submit Draft for Review | POST | /api/v1/content/{id}/submit-review | ContentWorkflowService.ts | { changelog: string } | Moves state to 'submitted_for_review'; triggers reviewer alert
Review Workflow | Reviewer Queue List | GET | /api/v1/content/review-queue | ContentWorkflowService.ts | Query: priority, submittedBy, page | Pending queue of courses & assets needing review
Review Workflow | Reviewer Action (Approve / Request Changes) | POST | /api/v1/content/{id}/workflow/action | ContentWorkflowService.ts | { action: 'approve' ¦ 'request_changes' ¦ 'reject', comment: string } | Updates workflow state; stores review comment in audit log
Review Workflow | Admin Final Publish Action | POST | /api/v1/content/{id}/publish | ContentWorkflowService.ts | Gated to Admin / Super Admin | Moves state to 'published'; increments major/minor version
Review Workflow | Workflow Audit Trail History | GET | /api/v1/content/{id}/workflow/history | ContentWorkflowService.ts | - | Timeline of all state changes, timestamps, and actors
Versioning & Lifecycle | Fetch Course Version History | GET | /api/v1/content/{id}/versions | ContentLifecycleService.ts | - | List of versions (v1.0, v1.1, v2.0) with publisher and date
Versioning & Lifecycle | Semantic Diff Between Versions | GET | /api/v1/content/{id}/diff | ContentLifecycleService.ts | Query: v1, v2 | Side-by-side diff of sections, blocks, and metadata
Versioning & Lifecycle | Rollback to Prior Version | POST | /api/v1/content/{id}/rollback/{versionId} | ContentLifecycleService.ts | versionId path param | Restores prior snapshot to active Draft
Versioning & Lifecycle | Archive / Soft-Delete Content | PUT / DELETE | /api/v1/content/{id}/lifecycle | ContentLifecycleService.ts | { action: 'archive' ¦ 'soft_delete' ¦ 'restore' } | Updates Lifecycle State; moves to archive or trash
Analytics & Dashboard | Executive Operational Overview KPIs | GET | /api/v1/analytics/dashboard/overview | DashboardService.ts | Query: period (7d ¦ 30d) | { totalUsers, dauMau, completionRate, publishedCount, pendingReviews }
Analytics & Dashboard | SDBV Geographic Heatmap | GET | /api/v1/analytics/dashboard/sdbv-heatmap | DashboardService.ts | Query: stateId, metric ('activity' ¦ 'completion') | GeoJson / aggregated metric counts per district/block
Analytics & Dashboard | Learner Progress Deep-Dive | GET | /api/v1/analytics/reports/learner-progress | AnalyticsService.ts | Query: sdbv, cohortId, dateRange, page | Paginated per-learner progress, completion, score matrix
Analytics & Dashboard | Cohort Completion & Retention Funnel | GET | /api/v1/analytics/reports/cohort-completion | AnalyticsService.ts | Query: cohortId | Completion %, average score, funnel stages (Enrolled -> Started -> 50% -> Done)
Analytics & Dashboard | Assessment Question Discrimination | GET | /api/v1/analytics/reports/assessment-analytics/{id} | AnalyticsService.ts | assessmentId path param | Question-level difficulty, pass rate, distractor frequency
Analytics & Dashboard | Export Reports to CSV / Excel | POST | /api/v1/analytics/reports/export | ReportExportService.ts | { reportType, filters, format: 'csv' ¦ 'xlsx' } | Binary stream of requested report file

## Scope Traceability Matrix
Scope Domain | Scope Feature Item (User Request) | Mapped Implementation Day | UI Screen / Component | API Service in swadhaar-admin-repo | Status in Plan
Admin Module | Admin UI branding & theming to Swadhaar | Day 1, Day 2 | customTheme.tsx, LogoIcon.tsx, Header.tsx | TenantService.ts | ✅ Planned
Admin Module | Admin login with OTP (same flow as learner) | Day 3 | /pages/login.tsx, RouteGuard.tsx | LoginService.ts | ✅ Planned
Admin Module | Role & Access Management (RBAC) | Day 4 | /pages/access/permissions.tsx, PermissionGate.tsx | RbacService.ts | ✅ Planned
Admin Module | User Management — mandatory phone, gender optional, SDBV hierarchy, bulk user creation, group SDBV filter | Day 5, Day 6 | /pages/users/index.tsx (N1), UserModal (P2), UserProfile (P3), BulkUpload (N2) | UserService.ts, BulkUserService.ts, MasterDataService.ts | ✅ Planned
Admin Module | Cohort / Group Management (SDBV, Course mapping, 2-panel builder, in-group roles) | Day 7, Day 8 | /pages/cohorts/index.tsx (N4), GroupBuilder (N7b), CohortDetail (N6) | CohortService.ts | ✅ Planned
Admin Module | Course & Question-Set form updates (new fields, tooltips, validations, Bloom tags) | Day 12, Day 14 | /content/courses/create (L2), /assessments/builder (L10) | ContentService.ts, AssessmentService.ts | ✅ Planned
Admin Module | Content-type & topic/subtopic filters (dynamic subtopic; show only uploaded types) | Day 10 | SDBVHierarchyFilter.tsx, TaxonomyFilterBar.tsx | TaxonomyService.ts, FrameworkService.ts | ✅ Planned
Admin Module | Notification / Alert Management (advanced - FCM, SMS, in-app bell, templates, rules) | Day 9 | /pages/notifications/index.tsx, NotificationComposer.tsx | NotificationService.ts, NotificationTemplateService.ts | ✅ Planned
Admin Module | Content authoring & upload UI (Creator role) | Day 12, Day 14 | /content/sections/[id]/edit (L4), MediaPicker (L4b) | ContentService.ts | ✅ Planned
Admin Module | Bulk content upload + validation (ZIP + metadata CSV, preview, error CSV) | Day 16 | /pages/content/bulk-upload.tsx | BulkContentService.ts | ✅ Planned
Admin Module | Archive & lifecycle UI (icon + column rename to Lifecycle State) | Day 12, Day 13, Day 18 | LifecycleChip.tsx, SwadhaarDataTable.tsx, CourseCatalog (L1) | ContentService.ts, ContentLifecycleService.ts | ✅ Planned
Content Module | Content taxonomy / topic-subtopic mapping (CRUD, drag-reorder, import, orphan check) | Day 10 | /pages/content/taxonomy.tsx | TaxonomyService.ts | ✅ Planned
Content Module | Content review & publish workflow (Creator -> Reviewer -> Publish, comments, audit) | Day 17 | /pages/content/review-queue.tsx, ReviewWorkspace.tsx | ContentWorkflowService.ts | ✅ Planned
Content Module | Content versioning, archive & delete lifecycle (versions, diff viewer, rollback) | Day 18 | /pages/content/courses/[id]/versions.tsx, TrashBin.tsx | ContentLifecycleService.ts | ✅ Planned
Content Module | Media handling (uploaded/YouTube video, assessments, PDFs, image crop) | Day 15 | /pages/content/library/videos.tsx (L11/L5), PDFs (L12/L5b) | MediaService.ts | ✅ Planned
Content Module | Content-type configuration & metadata forms (dynamic JSON schema renderer) | Day 11 | /pages/content/content-types.tsx, DynamicMetadataForm.tsx | ContentTypeService.ts | ✅ Planned
Analytics Module | Admin Dashboard (operational overview - 8 KPI cards, SDBV heatmap, top courses) | Day 19 | /pages/dashboard.tsx (SwadhaarStatCard, SDBVHeatmap) | DashboardService.ts | ✅ Planned
Analytics Module | Analytics Dashboard (deep dive - learner progress, cohort completion, question stats, export) | Day 20 | /pages/analytics/index.tsx, ReportExportModal.tsx | AnalyticsService.ts, ReportExportService.ts | ✅ Planned